## Project Plan
Week | Frontend | CI / CD
2022-04-18 | Concept | Create GH
2022-04-25 | Setup local demo | Create Devops Org
2022-05-02 | Setup local tests | Setup pipelines
2022-05-09 | Setup flask | Github Actions
2022-05-16 | Setup prediction service | Tests in Github
2022-05-23 |  | Azure setup
2022-05-30 |  | CD pipeline to Azure
| Goals | Goals
Flask webserver for local development
Prediction service running
Website running

## Project Infos
Trello Board | https://trello.com/b/EwIOnB9G/udacity-devops