## Project Plan
Week | Frontend | Difficulty | CI / CD | Difficulty
2022-04-18 | Concept | Easy
| Create Github Repo | Easy
| Create Azure & Azure Devops Org | Easy
2022-04-25 | Setup local demo | Easy
| Setup local tests | Easy
| Setup flask | Medium
2022-05-02 | Setup local tests | Medium
| Setup CI with Github Actions | Medium
2022-05-09 | Setup flask | Easy
| Tests in Github | Medium
2022-05-16 | Setup prediction service via Azure App Service | Medium
| Setup CD Pipeline in Azure | Hard
2022-05-23 | Create Documentation | Medium
Create Demo
2022-05-30 | Publish Project | Medium
| Goals |  | Goals
Flask webserver for local development
Prediction service running
Website running
CI/CD working
Submit project
Yearly Plan
Update dependencies for compliance
Move to Github.com for CD

## Project Infos
Trello Board | https://trello.com/b/EwIOnB9G/udacity-devops